Internship Overall Summer Plan

|  |  |
| --- | --- |
| **Week** | **Big Tasks** |
| **1**June 21st | * Get to Know Extension – Research assignment
* Lead Xanpasuchil activity
* Rinehart Clinic
* June Dairy Parade
 |
| **2**June 28th | * Lead 20-30 min game
* [Review the Tillamook County Community Health Needs Assessment](https://www.adventisthealth.org/documents/community-benefit/2019-chna/Tillamook_2019_CommunityHealthNeedsAssessment.pdf)
* [Prepare for trail mix demo](https://www.foodhero.org/recipes/do-it-yourself-trail-mix)
 |
| **3**July 5th | * Trail mix demo
* Prepare for First Aid demo
 |
| **4**July 12th | * First Aid demo
* Help coordinate Family night
 |
| **5**July 19th | * [Schedule](https://audubon.maps.arcgis.com/apps/dashboards/689df76c550b41bb92cfe6fd01278544) 1:1 meetings with Health Navigators
 |
| **6**July 26th | * Read through vaccination information documents
* Meet with Health Navigators
 |
| **7**August 2nd | * Lead a group with planning a part of family night
 |
| **8**August 9th | * Sign up for some fair activities
* Create the exit survey
 |
| **9**August 16th | * County Commissioners Presentation
* Begin writing a report to summarize the Juntos Afuera program, including doing an exit interview with each participant about their experience.
* [Here is a link to a sample report from previous internship](https://oregonstate.box.com/s/cdndcmaaco4mzoic5ag2i26xmwq22a6f)
 |
| **10**August 23rd | * Zipline!
* Continue writing a report to summarize the Juntos Afuera program, including doing an exit interview with each participant about their experience.
 |